## Slide 1: C-Aware update January 2011
Ben Bedwell

## Slide 2: Agenda
Introduction to new researchers at University of Nottingham
Introduction to new researchers at University of Cambridge
Reminder of project plan
Current state of trial infrastructure in Nottingham; plans for Cambridge and China
Plans for paper-prototyping
Current state of business model work
Other business

## Slide 3: New researchers

## Slide 4: New researchers
University of Nottingham
  Alexa Spence (Horizon Transitional Fellow)
  Caroline Leygue (Horizon Research Fellow)

## Slide 5: New researchers
University of Nottingham
  Alexa Spence (Horizon Transitional Fellow)
  Caroline Leygue (Horizon Research Fellow)
  Psychology research related to Energy
    Framing energy use and behaviour change
      Online energy experiment
      University student survey

## Slide 6: New researchers
University of Nottingham
  Alexa Spence (Horizon Transitional Fellow)
  Caroline Leygue (Horizon Research Fellow)
  Psychology research related to Energy
    Framing energy use and behaviour change
      Online energy experiment
      University student survey
  James Colley (Computer Science PhD student)
  Ian Dent (Computer Science PhD student)
  Jianhua Shao (Horizon PhD student)

## Slide 7: New researchers
University of Cambridge
  Gerard Briscoe (RA)
    Sustainable computing (business models/economics)

## Slide 8: Project plan

## Slide 9: Architecture - monitoring
Individual appliance monitors
Staff movement monitors
Mains utility monitors

## Slide 10
Architecture - monitoring
Data transfer
Hub

## Slide 11
Architecture - monitoring
Data store

## Slide 12: Architecture - monitoring
Data store
End-user Interfaces
User interfaces are accessed by displays with web access

## Slide 13: Architecture - presentation
Web access via mobile network
Web access via workplace
Internal LAN
UI3
UI1
UI2

## Slide 14: Architecture - presentation
UI3
UI1
UI2

## Slide 15: Architecture - presentation
User Interfaces
Who are the end users?
  Staff/tenants of a workplace – UI 1: Public display
  Managers of a workplace – UI2: Private desktop display
  Maintenance – UI3: Personal mobile display
There are 3 interesting interfaces that could be designed for these users, each with different characteristics

## Slide 16: Field trials
Eventual deployment of monitoring/presentation infrastructure on sites in UK and in China
  University of Nottingham
    Horizon (+ Computer Science?)
  China Mobile Research
  University of Cambridge
    Computer Science

## Slide 17: Research Qs
Human: what representations of information are most effective for encouraging energy-related behaviour change?
  Visual style, metaphor, units of information, etc.
  How does context affect this (culture, organisational structure, social relationships, time of day, etc.)?
Infrastructure: what infrastructure is necessary for this to happen?
Business: who pays for this infrastructure/how is value recovered and delivered?

## Slide 18: Work plan
Phase | Months |  |  |  |  |  |  | 
 | 1-3 | 4-6 | 7-9 | 10-12 | 13-15 | 16-18 | 19-21 | 22-24
1 |  |  |  | Develop/test monitoring hardware |  |  |  | 
2 |  |  |  |  | Develop/test data store |  |  | 
3 |  |  |  |  |  | Prototype UIs |  | 
4 |  |  |  |  |  | Develop/test control |  | 
5 | Prototype enhanced UIs |  |  |  |  |  |  | 
6 | Formal field trials |  |  |  |  |  |  | 
7 | Analysis |  |  |  |  |  |  | 

## Slide 19: Current trial infrastructure

## Slide 20: Update: trial infrastructure
Phase 1 – Testing monitoring architecture
  Consultation with University of Nottingham regarding current monitoring capabilities – done
    Building management system monitors one electricity meter per building (current power reading every few minutes)
    Access to current/historical data, although needs work to convert into useful format
  Acquiring suitable sensors and sensor hub
    Equipment purchased from Green Energy Options; waiting for installation
  Deploying and testing sensor infrastructure in test site
    Waiting for installation of monitoring equipment

## Slide 21: Monitoring equipment
Purchased from Green Energy Options
  Domestic energy sensors + displays (>1 million sold)
  Commercial + bespoke energy sensors + displays
Equipment for 4 domestic deployments and 1 workplace deployment
  Allows 4 members of Horizon staff to monitor their energy use at home, at work and while travelling (via mobile phone)
This is small scale, but allows us to test feasibility (and change design if necessary) before final field trials

## Slide 22: Monitoring equipment
Domestic deployments (x4):
  1 hub
  5-10 individual appliance monitors
  Circuit monitors (lighting, etc.)
Workplace deployment (Horizon):
  1 hub
  20 individual appliance monitors
  Circuit monitors
All sensors produce power data every 15 seconds, connect to hub via PowerLine (ethernet over power), hub connects to web via LAN

## Slide 23: Update: trial infrastructure
Phase 2 – Testing data store for monitoring
  Developing schema for data store
    Initial schema developed and updated following TEDDI workshop in December
  Deploying data store on suitable web platform
    Defined Amazon EC2 + MySQL DB as initial candidate
  Linking sensor infrastructure to data store and testing scalability of data store for long-term monitoring
    Waiting for installation of monitoring equipment

## Slide 24: Monitoring data store
Schema based on data produced by other domestic monitoring products (will be clarified when access is provided to Green Energy Options API)
Discussed at TEDDI workshop (aiming towards a common schema for all TEDDI-funded projects)
Includes:
  directory of hubs and sensors
    Including connection type, data units, sample frequency, accuracy, etc.
  log of hub and sensor events
    Including energy data from sensors, switch on/off, commission/decommission, etc.

## Slide 25: Monitoring data store
Aim for open APIs to access/insert data
Introduce mechanisms for controlling access, inspired by Dataware (Personal Container) research

## Slide 26: Prototyping plans

## Slide 27: Update: paper prototyping
Phase 3 – Prototype user interfaces
  Paper prototyping workplan defined

## Slide 28: Paper prototyping
Activities:
  Identify suitable participants (January)
    Represent end-users of the system
  Preparation exercises (late Jan-early Feb)
    3-4 creative exercises over 2 weeks
    Short (<15 minutes)
    Personal (no need for researchers to help; feedback by email/phone)
    20-30 participants
    Help designers to find out how end-users understand energy concepts, energy infrastructure and potential system features BEFORE paper-prototyping workshop

## Slide 29: Paper prototyping
Activities:
  ‘Expert’ design session (mid Feb)
    Combine energy and user-interface researchers in Horizon
    Use existing energy applications and feedback from preparation exercises to generate a set of basic designs for paper-prototyping workshop
      Small number of very simple visualisations
      Cover a wide range of potential visualisations (to encourage creative thinking)
      ‘Unfinished’ (to encourage criticism and initiative)

## Slide 30: Paper prototyping
Activities:
  Paper-prototyping workshop (late Feb-early March)
    In China
    12-15 participants (from participants of preparation exercises)
    Split into 3 groups
    Often produces better results when groups are mixtures of different types of user
    Use designs from ‘expert’ session as starting-points
    Criticise/modify initial designs
    Produce new designs
    Present designs to other groups for discussion

## Slide 31: Paper prototyping
Similar activities will be carried out in UK very soon
  Practice
  Jian’s Horizon project (cross-cultural design practices)
First major step in prototyping process: provides set of designs to be developed further
Immediate task:
  Identify stakeholders in China Mobile & Cambridge
    Understand organisational structure (in comparison to Horizon)
    Identify contacts for preparation and paper-prototyping activities
    Determine suitable dates for exercises

## Slide 32: Business model work

## Slide 33: Business models
Irene/Gerard … survey, etc.

## Slide 34: Other business

## Slide 35: Other business
Progress with MoU/other contractual issues
Progress with hiring further staff
  Cambridge
  Nottingham
Confirm next video-conference/workshop dates
  12th January 2011 8 a.m. GMT – videoconference
  March – paper-prototyping workshop, Beijing
  5th May 2011 – workshop (Nottingham)
  15th July 2011 8 a.m. GMT – videoconference
  27th-29th September 2011 – trials kick-off